## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 60 x 2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10
|  |  |  | 120 | 111 | 102 | 93 | 84 | 75 | 66 | 57 | 48 | 39 | 30 | 21 | 12 | 3 | Ideal Burndown
|  |  | 120 | 120 | 113.5 | 108 | 103 | 93 | 87 | 78 | 60 | 54 | 48 | 39 | 33 | 20 | 0 | Remaining Hrs (Total)
Implement APIs | Set up MySQL Database | JunTeng | 10 | 10 | 10 | 10 | 9 | 7 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement Card API | Jia | 10 | 10 | 10 | 10 | 9 | 9 | 9 | 5 | 4 | 4 | 4 | 3 | 3 | 2 | 0
| Implement User API | Ying | 15 | 15 | 14 | 13 | 12 | 11 | 10 | 8 | 6 | 4 | 2 | 2 | 2 | 2 | 0
| Implement Order & Payment API | JunTeng | 20 | 20 | 17.5 | 15 | 15 | 10 | 8 | 8 | 7 | 7 | 6 | 5 | 5 | 3 | 0
| Implement Map API | Jia | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 9 | 9 | 5 | 4 | 3 | 0
| Deploy to Amazon AWS | JunTeng | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 8 | 6 | 5 | 0
| Write Agile related Documentation | Ying | 15 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 0
Implement Web Client | Implement screens based on UI wireframes | Jia | 15 | 15 | 13 | 12 | 11 | 10 | 9 | 8 | 5 | 4 | 3 | 2 | 1 | 0 | 0
| Deploy client to Heroku | Jia | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
| Complete Unit and Regression Testing | Ying | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 5 | 4 | 3 | 2 | 0
Team:
JunTeng Tan | 20 hours / Week
Jia Ma | 20 hours / Week
Ying Liu | 20 hours / Week
Total Available Hours During Sprint: | 120